## Sheet1
[7 empty] | Year 1 | [10 empty] | Year 2
|  |  |  | Semester 1 | [6 empty] | Semester 2 | [5 empty] | Semester 1 | [5 empty] | Semester2
Research Activities | September | October | November | December | January | February |  | Feburary | March | April | May | June | July | July | August | September | October | November | December | December | January | February | March | April | May
Analyze the research problem and completion of the concept
Analyze the research problems for accommodation anomalies
Identify the source of data for the research problem
Developing the solution concept and merging RAF rules with solution
Completion of data collection, data preparation, analysis
Collecting data, preparing the data, analysis
Finding out the important features from the data
Features engineering
Development and implement of algorithms for the classifier
Studying different classifier algorithms
Benchmark analysis of existing algorithms with the processed data
Developing the algorithm for the classifier to detect accommodation anomalies
Testing and evaluation
Testing the classifier, performing close test, open test to check the robustness
Report Writing